## Stakeholders
Stakeholder Register
<Program Name>
[6 empty] | Where are they now? |  |  |  |  | Where do we want them to be?
Stakeholder Name (Individual or Group) | Organization | Role | Power (H/M/L) | Interest (H/M/L) | Describe how they're impacted and what they're interests are | Unaware | Resistant | Neutral | Supportive | Leading | Not a priority | Supportive | Leading | Engagement Strategy | Engagement Tactics | Notes
Stakeholder 1 | External - Vendor | Client Relationship Manager | High | High | Committed to the project and wants to ensure the external resources his organization provides deliver on expectations |  |  |  |  | x |  |  | x | Manage Closely | Very frequent communication, invitations to join reviews of draft deliverables | Knows our IT Manager
Stakeholder 2 | Internal - Sales Group | Product Owner | Low | Low | Considering bringing the technology into their department in the years ahead |  |  | x |  |  | x |  |  | Monitor | Quarterly communication to share updates on business impact | Asked to participate in current rollout but declined to participate
Stakeholder 3 | Internal - HR | Training Manager | High | Low | Providing a 1 day training workshop on how to use the new technology |  | x |  | x |  |  | x |  | Keep satisfied | Weekly project status communication. | Their team will not use the new technology but the quality of the training provided will have a big impact on project success
Stakeholder 4 | Internal - Sales Group | Super User | Low | High | Part of the end user testing team |  |  | x |  |  |  |  | x | Keep informed | Involve in technology demos and all prototyping sessions. Ask for frequent feedback. | Will not be able to prevent the technology from being introduced but will have to use it once the project is complete