|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Code | Description | Predecessors | Relationship | Lead/Lag |
| 1 | Plan move | None |  | 0 |
|  1.1 | Contact Dion and Carlita | None |  | 0 |
|  1.2 | Host planning lunch | 1.1 | FS (Finish/Start) | 0 |
|  1.3 | Develop and distribute move schedule | 1.2 | FS | 0 |
|  1.4 | Make hotel arrangement in Atlanta | 1.1 | FS | 0 |
| 2 | Prepacking | None |  | 0 |
|  2.1 | Gather packing materials | None |  | 0 |
|  2.2 | Select moving van company and sign contract | None |  | 0 |
|  2.2.1 | Contact three moving van companies for bids | 1.3 | FS | 0 |
|  2.2.2 | Select company and negotiate a final price | 2.2.1 | FS | 0 |
|  2.2.3 | Sign moving contract | 2.2.2 | FS | 0 |
|  2.3 | Pack small, delicate items | 2.1 | FS | -1 |