## Risks
ID | Risk Name | Risk Description | Likelihood (value will be between 1-5) | Impact (value will be between 1-5) | Risk Value (Likelihood x Impact) | Priority (High, Moderate or Low) | Potential Root Causes | Triggers | Risk Response Strategy
WBS #3.1 | Job Offer Rescinded | John's new employer in Chicago could decide to cancel the job offer provided. This would mean John no longer has employment in the new city he is moving to. | 1 | 4 | 4 | Low | 1. New employer is attempting to check references but John's contacts are not responding to the calls. 2. John's new employer goes bankrupt. | 1. John's new employer isn't responding to John's phone calls and emails. 2. John's references have not been contacted 10 days after he signed the job offer. | Accept - low priority risk and should it materialize, John is confident he could find another job in Chicago. John checked the popular employment sites and found a number of vacancies for jobs he would be qualified for.
WBS #2.8 | Broken furniture | Some or all of John's furniture gets broken during the move. | 3 | 3 | 9 | Moderate | 1. Movers were not careful in packing. 2. Movers get into a car accident en route. | 1. Movers appear to be in a rush during packing. | Transfer - buy insurance to cover furniture loss.
WBS 4.2 | New apartment | Existing tenant in John's new apartment does not move out in time for John's arrival. | 4 | 5 | 20 | High | 1. Existing tenant is moving to another city and may not be in Chicago to ensure the apartment is emptied. | 1. One week before John is scheduled to move in, the tenant's belongings remain in the apartment. | Mitigate - offer to help the existing tenant pack; offer to hire additional help for the tenant; book a fully refundable hotel room in Chicago for 3 days to give the tenant a bit of extra time if needed.
For illustrative purposes, let's say the following prioritization has been established by the organiztion:
- risk values that are 6 or less, represent "low" priority
- risk values that are between 9 and 15 could be "moderate" priority
- risk values that are between 16 and 25 could be "high" priority